## ListOfFeatures
Product Backlog - Project Title (List of your features)
User Stories / List of features
As a site visitor, I am able to search for destinations by price and key words
As a site visitor, I am able to subscribe to newsletters to get notified when new trips are available.
As an online buyer, I am able to book trips on the website.
As a website user, I can fill out a contact form to ask for support.
As a user i can log in / sign in
As an admin I can add images to the gallery and add new trips
As an admin I am able to see users information
As a a user I am able to leave feedback of the trip
As a user I am able to see all my trips in the profile page
As a user I am able to change personal information about myself
As a user I am able to withdraw the booking

## sprint1
Sprint Backlog : Sprint 1 Feb 7 - Feb 11
BACKLOG TASK & ID | STORY POINTS (NR) | ASSIGNED TO | STATUS
User Story/ Header & Footer #1
Task : Header | 2 | Jarmila | Ongoing
Task : Footer | 2 | Mark | Ongoing
Task : Github repo | 4 | ALL | DONE
Task: Deploy static web | 2 | ALL
User Story #2 Booking |  | Mona
Task : user database
Task : make database blueprint
Task
Task
User Story #3 Contact Form |  | Mona
Task
Task
Task
Task
User Story #4 Search Bar |  | Jarmila
Task
Task
Task
Task
User Story #5 News Letter |  | Mark
Task
Task
Task
Task
TOTAL
Hints:
During this week, you should update your exisiting pages that is your pages have universarl header and footer.
Upload this excel file to your project Repo in GitHub and update it regulaly.
You have planned your features and have distributed work among your team members
You have designed your database. Make sure that each member has his/her own table to work with.
You have create a GitHub repo and each member is added as collaborator.
Please make regular commits and get familiar with the development activities by utilizing version control.
Uploaing your files to GitHub repo is not acceptable. It will have negative impact on your grade.
Ask questions during the consultation sessions if you are not sure about how you are proceeding

## sprint2
Sprint Backlog : Sprint 2 (Feb 14 - Feb 18)
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS
User Story #1
Task : Make a list of categories of products | 2 | Pekka | Ongoing
Task : List products based on categories | 2 | Juha
Task : Search products | 4 | Johanna
Task: Display products | 2 | Markku
User Story #2
Task
Task
Task
Task
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL
Hints:
You are working on tasks that you have been assigned to in your team.
You are present in your team meetings.
You are familiary with the GitHub repo for your project work.
You are doing regular commits and you have the latest version of the website in your local device.

## sprint3
Sprint Backlog : Sprint 3 (Feb 21 - Feb 25)
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS
User Story #1
Task : Make a list of categories of products | 2 | Pekka | Ongoing
Task : List products based on categories | 2 | Juha
Task : Search products | 4 | Johanna
Task: Display products | 2 | Markku
User Story #2
Task
Task
Task
Task
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL
Hints:
You are working on tasks that you have been assigned to in your team.
You are present in your team meetings.
You are familiary with the GitHub repo for your project work.
You are doing regular commits and you have the latest version of the website in your local device.
Finalize your work and start to preare for the project review.
Make sure that your repository, shell.hamk.fi servers all have the latest version of your website.